## File map
DSE 6100 Project 1: main files
What each main file in the project1 folder does and what it connects to (as of Oct 11, 2026).
Layer | File | Location | What it does | Talks to
Frontend | index.html | project1/Frontend/ | The login page: username and password boxes, Sign In and Register buttons, and a red error line. Its pattern rule blocks characters like ' and ;. | Loads index.js and stylesheets.css
Frontend | index.js | project1/Frontend/ | Sends the form to /update/Users/signIn or /insert/Users. On success it saves the session token in sessionStorage and redirects to the dashboard. | app.js (over HTTP); redirects to tableContents.html
Frontend | tableContents.html | project1/Frontend/ | The dashboard's skeleton: a welcome header, Sign Out and Delete Account buttons, and three empty tables (current user, all users, search results) with Previous/Next buttons. | Loads tableContents.js and stylesheets.css
Frontend | tableContents.js | project1/Frontend/ | Fills those tables. It loads all users 25 at a time, handles Sign Out and Delete Account, and sends users back to the login page if they have no token. The search options are defined in searchSelect, but nothing builds a search form from them yet. | app.js (over HTTP); imports constantsSQL.js
Frontend | stylesheets.css | project1/Frontend/ | Layout and look for both pages: the centered login card, table borders, pagination buttons. | Used by both HTML pages
Shared | constantsSQL.js | project1/Public/ | One shared list of names (table name, column names, the 8 search types, 25 rows per page), so the frontend and backend can't drift out of sync. | Imported by tableContents.js, app.js, dbService.js
Backend | app.js | project1/Backend/ | The server's front door. It defines every URL the frontend can call. When a user signs in it creates a random token and remembers which user it belongs to, so it can reject requests that don't carry a valid token. Every search goes through a single URL, /search/Users/actions, which picks the matching function from a lookup table. | Called by index.js and tableContents.js; calls dbService.js
Backend | dbService.js | project1/Backend/ | The only file that talks to MySQL. It cleans up user input, hashes passwords (PBKDF2 with a random salt), and runs every query with ? placeholders. It also builds the LIMIT/OFFSET paging. It has one function per feature. | Called by app.js; reads .env; queries the Users table
Backend | .env | project1/Backend/ | Database connection settings (host, user, password, database name, port), read by dbService.js at startup. | Read by dbService.js
Backend | package.json | project1/Backend/ | Lists the libraries (express, mysql, cors, dotenv, nodemon) and the npm start command. | Used by npm
Database | Users table | MySQL, web_app database | The actual data: username (primary key), password hash, first and last name, salary, age, registerday, signintime. | Queried by dbService.js
Files you can ignore
| File(s) | Location | Why
| oldIndex.html / oldIndex.js | project1/Frontend/ | The professor's starter demo page for the names table.
| names table + /insert, /getAll, /search/:name, /update, /delete routes | web_app database; app.js and dbService.js | Starter demo code, not part of Project 1's features.
| exercise1-3, nodejs_examples, react_examples, slides, SmartExcel, project2 | Repo root | Other course material that lives in the same repo.

## Checklist
DSE 6100 Project 1: remaining work checklist
Based on GitHub main as of commit 62ca90c (Oct 9, 2026). If your teammate has unpushed work, some items may already be done. Edit the Status (dropdown), Owner and Notes columns.
Progress
| Total items | 44 | Percent done | 34.09%
| Done | 15
| In progress | 0
# | Section | Item | Details | Status | Owner | Notes
1 | 1. Fixes to existing code | Search endpoint | app.js line 395: replace searchHandler with searchFunc and stop calling .then() on an awaited value. Every search returns error 500 until this is done. | Done
2 | 1. Fixes to existing code | Sign Out handler | tableContents.js line 284: add async. Done locally Oct 11, not yet committed. | Done
3 | 1. Fixes to existing code | Sign Out request | tableContents.js line 290: change PATCH to POST. | Done
4 | 1. Fixes to existing code | Salary range | dbService.js lines 558-577: declare queryParams, use Math.min/Math.max and BETWEEN. | Done
5 | 1. Fixes to existing code | Age range | dbService.js lines 596-613: same fix as salary; remove the ==. | Done
6 | 1. Fixes to existing code | Registered after john | dbService.js line 641: >= becomes >. | Done
7 | 1. Fixes to existing code | Same day as john | dbService.js line 673: rewrite the WHERE clause. | Done
8 | 1. Fixes to existing code | Never signed in | dbService.js line 698: = NULL becomes IS NULL. | Done
9 | 1. Fixes to existing code | Registered today | dbService.js line 724: check registerday = CURDATE(), not sign-in time. | Not started |  | Not sure what this means, we wouldn't use the registered date to find out users whom signed in today
10 | 1. Fixes to existing code | Name search | dbService.js line 509: CONCAT becomes CONCAT_WS so users with no last name still match. | Done
11 | 1. Fixes to existing code | Name route | app.js line 407: pass the page number first. | Done
12 | 1. Fixes to existing code | Profile update | dbService.js line 464: ALLOWED_UPDATE_SET becomes DbService.ALLOWED_USERS_UPDATE_SET. | Done
13 | 1. Fixes to existing code | Sign-in lookup | dbService.js line 364: LIKE ? becomes = ?. | Done |  | Not sure what this means, we do LIKE ? for a case insensitive search on username
14 | 1. Fixes to existing code | Sort column | dbService.js line 339: only accept real column names (SQL injection hole). | Done |  | Not sure what this is talking about; this is already the case
15 | 1. Fixes to existing code | Search labels | tableContents.js lines 47 and 55: 'same day as' and 'registered today'. | Done |  | Not sure what this is talking about
16 | 1. Fixes to existing code | Expired sessions | When a request returns 401, send the user back to the login page. | Not started
17 | 2. Database table and test data | Create the Users table | In phpMyAdmin, with password VARCHAR(255). With the README's VARCHAR(50), every registration fails with 'Data too long'. | Not started
18 | 2. Database table and test data | Insert about 15 test users | Varied salaries and ages; several registered the same day as one chosen user (feature 9); some before and after that user (feature 7); a few registered today (feature 10); some with signintime empty (feature 8). | Not started
19 | 2. Database table and test data | Register 2-3 users through the website | Test users inserted with SQL can't sign in, because their passwords aren't hashed. | Not started
20 | 3. Profile fields | Register form | index.html: add first name, last name, salary and age inputs. | Not started |  | Not necessary, we just edit after login
21 | 3. Profile fields | Register request | index.js line 60: send the four new fields along with the username and password. | Not started |  | Not necessary, we just edit after login
22 | 3. Profile fields | Register route | app.js line 146: read the new fields from the request. | Not started |  | Not necessary, we just edit after login
23 | 3. Profile fields | Insert query | dbService.js insertNewUser: accept the fields and add them to the INSERT. | Not started |  | Not necessary, we just edit after login
24 | 3. Profile fields | Optional: edit-profile form | On the dashboard, using the existing PATCH /update/Users route (needs the profile-update fix in section 1). | Not started |  | Necessary, we have to edit after login
25 | 4. Dashboard tables and pagination | Current-user table (top) | Fill it with the signed-in user's details; remove its Previous/Next buttons since it shows one row. | Not started
26 | 4. Dashboard tables and pagination | All-users pagination | tableContents.html line 34: rename the duplicate id to allUserDisplayTable-pagination so the existing buttons work. | Done
27 | 4. Dashboard tables and pagination | Search-results table (bottom) | Show whatever a search returns, with column headers that match the search. | Not started
28 | 4. Dashboard tables and pagination | Search-results pagination | Wire up Previous/Next to re-run the same search with the next page number. The backend already returns results 25 at a time. | Not started
29 | 4. Dashboard tables and pagination | Readable dates | Show 2026-10-11 instead of 2026-10-11T04:00:00.000Z, and sign-in times in local time. | Not started
30 | 5. Search panel | Panel markup | tableContents.html: a dropdown, an area for inputs, a Search button and an error line, above the search-results table. | Not started
31 | 5. Search panel | Dropdown | Build its options from searchSelect (tableContents.js lines 19-58). | Not started
32 | 5. Search panel | Inputs | When the choice changes, show the right input boxes for that search (none for features 8 and 10). See the Searches tab. | Not started
33 | 5. Search panel | Validation | Required boxes filled, numbers where needed, min not above max. | Not started
34 | 5. Search panel | Request | POST /search/Users/actions with action, page and params, sending the session token header. | Not started
35 | 5. Search panel | Results | Show them in the search-results table, 'No records found' when empty, and errors on the error line. | Not started
36 | 5. Search panel | Test all 8 searches | Against the test data; check every result by hand. | Not started
37 | 6. Deliverables | sql.txt | The CREATE TABLE Users, the test-data INSERTs, and the SQL behind each of the 10 features with example values. | Not started
38 | 6. Deliverables | Video, app part | Register, sign in, a rejected SQL-injection attempt, then all 8 searches with an explanation of each result. | Not started
39 | 6. Deliverables | Video, Git part | Local vs remote repositories, clone, pull, fetch, add, commit and push, shown by both teammates. | Not started
40 | 6. Deliverables | Real commits from both of you | Commit and push your share of this work so the history shows it (Khush's only commits so far are two Oct 5 tests). | Not started
41 | 6. Deliverables | Before recording | Stop the backend from printing the database password at startup (dbService.js line 15). | Not started
42 | 7. Optional cleanup | Remove debug routes | Remove /debug and /testdb from app.js. | Not started
43 | 7. Optional cleanup | Remove starter names code | oldIndex.html, oldIndex.js, and the names routes and functions. | Not started
44 | 7. Optional cleanup | Take .env out of the repo | Add it to .gitignore (it holds the database password). | Not started

## Search Panel
The 8 searches the panel needs
Options and inputs are defined in searchSelect (tableContents.js lines 19-58); action key = the value sent to POST /search/Users/actions.
Feature | Search | Inputs | Action key
3 | By first and/or last name | Name | searchByUsersName
4 | By username | Username | searchByUsersID
5 | Salary between X and Y | Min salary, max salary | searchBetweenUsersSalary
6 | Age between X and Y | Min age, max age | searchBetweenUsersAges
7 | Registered after a user | Username | searchUsersRegistrationAfterUserID
8 | Never signed in | None | searchNeverSignedInUsers
9 | Registered the same day as a user | Username | searchUsersRegistrationTimeSameAsUserID
10 | Registered today | None | searchUsersSignedInToday (rename suggested)